PAYMENT SCHEDULE

Partial payment will be made upon accomplishing the tasks and milestones and deliverables set in the table below.

The contractor is required to submit the following deliverables:

| # | Task /Milestone | Deliverable Outputs | Timeline | Payment (% USD) |
| --- | --- | --- | --- | --- |
| 1 | Inception phase Development of methodology, detailed workplan, stakeholder mapping, and identification of key assumptions and risks, including analytical approach to digital LSS systems and MIIEF integration | Inception Report | (10 days) | 10% |
| 2 | Workstream 1 Draft case study Desk review, analysis, and drafting of LSS systems, including digital learner profiling and MIIEF integration | Draft LSS Country Case Study | (30 days) | 20% |
| 3 | Workstream 1 and 2: Fieldwork (Crosscutting and Parallel) Conduct KIIs, FGDs, site visits (including MIIEF), and infrastructure audits; generates primary data feeding both the LSS case study and ECE tracker development | Fieldwork dataset and validated inputs | (30 days parallel with WS1 and WS2) |  |
| 4 | Workstream 2: Draft ECE Accountability Tracker (Parallel) Development of indicator matrix, monitoring framework, and draft guidance note based on emerging findings from WS1 | Draft ECE Accountability Tracker | (30 days; parallel with WS1 and fieldwork) | 15% |
| 5 | Workstream 1: Finalization Revision and refinement of the case study based on stakeholder feedback | Final LSS Country Case Study | (15 days) | 15% |
| 6 | Workstream 2: Finalization (Parallel) Pilot testing, validation, and refinement of the ECE Accountability Tracker and guidance note | Validated ECE Accountability y Tracker | (15 days; parallel with WS1 finalization) | 15% |
| 7 | Workstream 3: Investment Case Development of costing models, macroeconomic analysis, and PF4C fiscal space assessment | Disability Inclusive ECE Investment Case Report | (10 days) | 15% |
| 8 | Workstream 3: Policy Briefs and final consolidation of all deliverables - Preparation of advocacy-oriented outputs targeting Government and development partners/private sector - Final consolidation, quality assurance, and submission of all deliverables | - Two Policy Briefs - Consolidated deliverables package | (15 days) | 10% |

Note: During the period (30 working days), activities under Workstreams 1 and 2 will be implemented in parallel, allowing real-time integration of data collection, analysis, and tool development. Fieldwork is embedded within this same period and directly supports both the LSS Country Case Study (Workstream 1) and The ECE Accountability Tracker (Workstream 2)