PAYMENT SCHEDULE

Partial payment will be made upon accomplishing the tasks and milestones and deliverables set in the table below. 
 
The contractor is required to submit the following deliverables: 
	# 
	Task /Milestone  
	Deliverable 
Outputs  
	Timeline   
	Payment (% 
USD)  

	1 
	Inception phase  
Development of methodology, detailed workplan, stakeholder mapping, and identification of key assumptions and risks, including analytical approach to digital LSS systems and MIIEF integration  
	Inception Report  
	(10 days)  
	10%  


	2 
	Workstream 1 Draft case study  
Desk review, analysis, and drafting of LSS systems, including digital learner profiling and MIIEF integration  
	Draft 	LSS 
Country 
Case Study  
	(30 days)  
	20%  
  

	3 
	Workstream 1 and 2: Fieldwork (Crosscutting and Parallel)  
Conduct KIIs, FGDs, site visits (including MIIEF), and infrastructure audits; generates primary data feeding both the LSS case study and ECE 
tracker development  
	Fieldwork dataset and validated inputs  
	(30 days parallel with WS1 and 
WS2)  
	

	4 
	Workstream 2: Draft ECE 
Accountability Tracker (Parallel)  
Development of indicator matrix, monitoring framework, and draft guidance note based on emerging findings from WS1  
	Draft 	ECE 
Accountability Tracker  
	(30 days; parallel with WS1 and 
fieldwork)  
	15%  


	5 
	Workstream 1: Finalization   
Revision and refinement of the case study based on stakeholder feedback   
	Final 	LSS 
Country 
Case Study  
	 (15 days)  
	15%  


	6 
	Workstream 2: Finalization (Parallel) Pilot testing, validation, and refinement of the ECE Accountability Tracker and guidance note  
	Validated 
ECE 
Accountability y Tracker  
	(15 days; parallel with WS1 
finalization)  
	15%  


	7 
	Workstream 3: Investment Case   
Development of costing models, macroeconomic analysis, and PF4C 
fiscal space assessment  
	Disability Inclusive 
ECE 
Investment 
Case Report  
	 (10 days)  
	15%  


	8 
	Workstream 3: Policy Briefs and final consolidation of all deliverables 
· Preparation of advocacy-oriented outputs targeting Government and development partners/private sector 
· Final consolidation, quality assurance, and submission of all deliverables  
	· Two Policy 
Briefs  
· Consolidated deliverables package  
	(15 days)  
 
  
	10%  



 	 
Note: During the period (30 working days), activities under Workstreams 1 and 2 will be implemented in parallel, allowing real-time integration of data collection, analysis, and tool development. Fieldwork is embedded within this same period and directly supports both the LSS Country Case Study (Workstream 1) and The ECE Accountability Tracker (Workstream 2) 

